## Slide 1: Form Contract Modifications
A Subcontractor’s Perspective

## Slide 2: In this presentation
What you Should Be Looking for when reading a proposed subcontract
what you should be considering when reading key provisions
How you should protect yourself in a subcontract

## Slide 3: Subcontracts Generally
Identify the parties accurately
1
Identify the Owner accurately
2
Identify the Project accurately
3
Identify a start date and/or a starting condition (NTP etc.)
4

## Slide 4: Form Contracts
AIA A401 - 2017
Published by the American Institute of Architects with input and endorsement from several trade organizations and industry stakeholders
Because they are drafted by architects, the architect plays a large role in construction project administration
Each document is updated every 10 years
ConsensusDOCS 750 (2017)
Developed by a collection of trade organizations and construction industry stakeholders, including the ASA, ABC, AGC,
First created in response to the 2007 update to the AIA contracts updated that year
Each document is updated on an as-needed basis

## Slide 5: Subcontract Documents
AIA A401 - 2017
Addressed in Articles 1 and 15
Does not include the Subcontractor’s Proposal
Prime contract incorporated
Requires Contractor to provide copy of all Subcontract Documents prior to execution
ConsensusDOCS 750 (2017)
Addressed in Articles 2.4, 2.6.1, and 13
Does not include the Subcontractor’s Proposal
Prime contract incorporated
Requires Contractor to provide copy of all Subcontract Documents prior to execution
Contains an express Order of Precedence

## Slide 6: Subcontract Documents Considerations
Ensure your proposal is included and/or that your scope of work is clearly set forth
Ensure that the only incorporated documents are ones that you have been provided
Ensure you review the most important provisions of the prime contract
Ensure you know the order of precedence

## Slide 7: Contractor’s Responsibilities
AIA A401 - 2017
Addressed in Article 3
ConsensusDOCS 750 (2017)
Addressed in Article 4

## Slide 8: Contractor’s Responsibilities Considerations
Identify the Contractor’s representative and their scope of authority for the Project
Ensure the Contractor’s communication obligations are set forth, especially concerning Subcontractor’s lien rights
Clearly outline the requirement for the Contractor to provide storage areas on the Project
Clearly outline Contractor’s responsibility for scheduling

## Slide 9: Payments to Subcontractor
AIA A401 - 2017
Addressed in Article 11
ConsensusDOCS 750 (2017)
Addressed in Article 8

## Slide 10: Payment Defaults
AIA A401 - 2017
Schedule of Values to be submitted prior to first application for payment
Does not contain “pay-if-paid” language per §11.1.3 last sentence
Provides for retainage and late payment interest
ConsensusDOCS 750 (2017)
Schedule of Values is a condition precedent to payment (must be provided within 15 days of execution)
Does not contain “pay-if-paid” language per 8.2.5
Provides for retainage and late payment interest

## Slide 11: Payment Considerations
Be aware of attempts to add “pay-if-paid” language
Confirm retainage
Under both form contracts, payment is triggered by Application for Payments

## Slide 12: Indemnity
AIA A401 - 2017
Addressed in Article 4.7
ConsensusDOCS 750 (2017)
Addressed in Article 9.1

## Slide 13: Indemnity Defaults
AIA A401 - 2017
Subcontractor shall indemnify and hold harmless
Indemnified parties: Owner, Contractor, Architect, Architect’s consultants, and agents and employees
Bodily injury, sickness, disease or death, or to injury to or destruction of tangible property (other than the Work itself),
To the extent caused by the negligent acts or omissions of the Subcontractor, Sub-subcontractors, anyone directly or indirectly employed by them, or anyone for whose acts they may be liable
Regardless of whether or not such claim, damage, loss, or expense is caused in part by a party indemnified by Subcontractor.
ConsensusDOCS 750 (2017)
Subcontractor shall indemnify and hold harmless
Indemnified parties: Constructor, Design Professional, Owner, and their agents, consultants, and employees
Bodily injury and property damage other than the Work itself
To the extent caused by the negligent or intentionally wrongful acts or omissions of Subcontractor, sub- subcontractors, or anyone employed directly or indirectly by any of them or by anyone for whose acts any of them may be liable

## Slide 14: Indemnity Considerations
Be aware of the breadth of indemnity including the nature of the claims and the parties indemnified
Be sure to only indemnify for your own negligence
Be aware that some indemnity provisions are unenforceable in certain jurisdictions

## Slide 15: Delay/Force Majeure
AIA A401 - 2017
No express provision regarding delays or force majeure
Subcontractor may make claims for extensions of time and damages for delay (Article 5.3)
ConsensusDOCS 750 (2017)
Delays addressed in Article 5.3
Subcontractor agrees to initiate all claims for which Owner is or may be liable in the manner and within the time limits provided in the Subcontract Documents for like claims by Constructor upon Owner
Subcontractor may recover for delay damages caused by Contractor
No express force majeure provision

## Slide 16: Delay/Force Majeure Considerations
Be aware of notice requirements, including those contained in the Prime Contract
Document delays and their causes carefully

## Slide 17: Unknown Site Conditions
AIA A401 - 2017
Not addressed
ConsensusDOCS 750 (2017)
Addressed in Article 7.3
Subcontractor to stop affected Work after the condition is first observed and give prompt written notice of the condition to Constructor.
Subcontractor shall not be required to perform any Work relating to the condition without the written mutual agreement of the Parties

## Slide 18: Unknown Site Conditions Considerations
Ensure this is addressed in the Subcontract
You should try to avoid being responsible for unknown site conditions

## Slide 19: Termination of Subcontract
AIA A401 - 2017
Addressed in Article 7
ConsensusDOCS 750 (2017)
Addressed in Article 10

## Slide 20: Termination of Subcontract Defaults
AIA A401 - 2017
Subcontractor may terminate for the same reasons as the Contractor may terminate with Owner under the Prime Contract, or for non-payment ≥ 60 days
Contractor may terminate for cause and finish Subcontractor’s scope
No Contractor right to terminate for convenience
In the event the Owner terminates Prime Contract for convenience, Subcontractor entitled to payment on work performed and overhead and profit on work not performed
Contractor may suspend, Subcontractor receives equitable adjustment in time and sum
ConsensusDOCS 750 (2017)
Subcontractor may terminate after stopping work for 30 days due to non-payment or “unreasonable” suspension
Subcontractor type of recovery dependent on payment status of Owner to Contractor
Contractor may terminate for cause and finish Subcontractor’s scope utilizing Subcontractor’s material and supplies; Subcontractor may no unreasonably withhold consent for Contractor to utilize Subcontractor’s tools and equipment onsite
If Owner terminates Prime Contract, Subcontractor recovery limited
Wrongful termination by Contractor results in Subcontractor recovering reasonable overhead and profit on the Subcontract Work not executed

## Slide 21: Termination of Subcontract Considerations
Be aware of attempts to add termination for convenience language
Be aware of attempts to increase Contractor’s rights to suspend
Be aware of attempts to limit Subcontractor’s remedies
Be aware of attempts to increase Contractor’s remedies
Be aware of all notice requirements

## Slide 22: Dispute Resolution
AIA A401 - 2017
“Contractor’s Claims” addressed in Article 3.4 and 3.5
Claims and Disputes addressed in Article 6
ConsensusDOCS 750 (2017)
Addressed in Article 11

## Slide 23: Dispute Resolution Defaults
AIA A401 - 2017
AAA Mediation is a condition precedent to binding dispute resolution
Binding dispute resolution is to be selected (Litigation is default)
Expressly provides for consolidation and joinder
Silent as to attorney’s fees
ConsensusDOCS 750 (2017)
Direct Discussiona are required before mediation
Mediation is the second step (Default is AAA but other options provided)
Binding dispute resolution is to be selected (Litigation is default)
Prevailing party awarded costs and attorney’s fees

## Slide 24: Dispute Resolution Considerations
Be aware of notice and appeal requirements, especially timeframes
Be aware of attempts to permit the contractor to determine dispute resolution path
Be aware of attempts to change venue of dispute resolution
Be aware of attempts to shift costs of dispute resolution

## Slide 25: Liquidated Damages
AIA A401 - 2017
Addressed in Article 3.4.1
Liquidated damages are only applied if “assessed” against the Contractor
ConsensusDOCS 750 (2017)
Addressed in Article 5.5
Liquidated damages are only applied if “assessed” against the Contractor

## Slide 26: Liquidated Damages Considerations
Be aware of any liquidated damages provision in the Prime Contract
Be sure to limit liquidated damages to those actually “assessed” against the Contractor
Ensure subcontracts limit liquidated damages against the subcontractor to the Subcontractor’s share of the responsibility for the damages

## Slide 27: Waiver of Consequential Damages
AIA A401 - 2017
Addressed in Article 6.4
Exception for liquidated damages
ConsensusDOCS 750 (2017)
Addressed in Article 5.4
Exception for any liquidated, consequential, or other damages that Owner is entitled to recover against Constructor under the prime agreement and for losses covered by insurance as required by the subcontract
Requires similar waivers in all sub-subcontracts

## Slide 28: Waiver of Consequential Considerations
Major difference between ConsensusDOCS and AIA
Be aware of major exception to waiver contained in the ConsensusDOCS
Owner is the most likely party to suffer significant consequential damages

## Slide 29: Final Thoughts
Always be aware of Subcontract timing and notice requirements
Paper, paper, paper
“An ounce of prevention is worth a pound of cure”

## Slide 30: Thank you
mfelezzola@babstcalland.com