## Slide 1: American Subcontractors Association Delay and Disruption Claims: Key Elements and Considerations
By Jim Sienicki and Ed Hermes
jsienicki@swlaw.com
(602)-382-6351
ehermes@swlaw.com
(602)-382-6529

## Slide 2: Delay v. Disruption Claims
“The Court described the difference as follows: Although the two claim types often arise together in the same project, a ‘delay’ claim captures the time and cost of not being able to work, while a ‘disruption’ claim captures the cost of working less efficiently than planned.” Bell BCI Co. v. United States, 81 Fed. Cl. 617, 636 (2008), aff'd in part, vacated in part, remanded, 570 F.3d 1337 (Fed. Cir. 2009) (citations omitted).

## Slide 3: Elements of Delay and Disruption Claims
“The contractor must prove for either claim the elements of liability, causation, and resultant injury. . . When the contractor is asserting a delay claim, the contractor has the burden of showing the extent of the delay, that the delay was proximately caused by government action, and that the delay caused damage to the contractor. . . .” Bell BCI Co. v. United States, 81 Fed. Cl. 617, 636 (2008), aff'd in part, vacated in part, remanded, 570 F.3d 1337 (Fed. Cir. 2009) (citations omitted).

## Slide 4: COVID-19, Labor Shortages, Supply Issues
Depending on subcontract terms, incorporated prime contract terms, and the impact the COVID-19 pandemic, and/or unforeseen supply chain disruptions had on a specific project, the resulting effects may be considered a force majeure, delay, change in law, suspension, cost escalation and/or other applicable event.
Subcontractors may be able to use these clauses or (not as good) the commercial impracticability, frustration of purpose and/or impossibility of performance defenses to excuse late completion due to the COVID-19 pandemic and/or supply or labor disruptions and may possibly have claims for delay and/or disruption due to increased costs.

## Slide 5: Force Majeure and COVID-19
Some Prime Contracts direct that a contractor, and by extension subcontractors, who are excused by a force majeure or other applicable clause from liability to the owner for late performance are entitled to a non-compensable extension of time.
Subcontractors may be protected from claims for liquidated or actual damages arising out of delays caused by late performance related to COVID-19 or other unforeseeable labor or material shortages, but must bear their own costs to staff the project for longer than planned and budgeted.
Because COVID-19 (and related shortages) have been unprecedented and is still an ongoing issue in the construction industry, subcontractors should consider closely reviewing and updating their contracts with regard to provisions that are favorable (and unfavorable) to them on these issues.

## Slide 6: Delay Claims
Four things to consider:
  Excusability
  Compensability
  Criticality
  Concurrency

## Slide 7: Excusable
“REL, as the contractor justifying untimely performance, had the burden of proving delay and of proving that any delays in performance were excusable. . . .Pursuant to the terms of the contract, a delay is excusable when it is due to ‘unforeseeable causes beyond the control and without the fault or negligence of the Contractor.’” Richard E. Lambert, Ltd. v. City of Tucson Dep't of Procurement, 223 Ariz. 184, 188, 221 P.3d 375, 379 (Ct. App. 2009) (citations omitted and emphasis added).

## Slide 8: Critical
For a subcontractor to obtain a time extension or additional compensation for extended performance, the delay must affect overall project completion. The delay must be critical.

## Slide 9: Delays Caused By Material Shortages
Subcontractors are facing unprecedented price escalation and material shortages.
Depending on the length and type of shortage and the terms of the contract, including cost escalation clauses, these delays and cost escalations may be compensable with time or money depending on foreseeability, impact, and specific contract terms.
Watch out for no damages for delay or disruption clauses.

## Slide 10: ConsensusDocs® 200.1 Time and Price-Impacted Materials Contract Amendment
Identifies Potentially Time and Price Impacted Material
Identifies Baseline Price
Provides for “equitable adjustment” to Contract Price upon timely notice and substantiation
Adjustment to Contract Price may be increase or decrease
Caps percentage of adjustment
No contractor liability for delay in delivery not the fault of contractor

## Slide 11: ConsensusDocs® 200.1 (Cont’d) (emphasis added)
1. POTENTIALLY TIME AND PRICE-IMPACTED MATERIAL As of the date of this Amendment, certain markets providing essential materials to the Project are experiencing or are expected to experience significant, industry-wide economic fluctuation during the performance of this Agreement that may impact price, availability and delivery time frames ("Potentially Time and Price-Impacted Material"). This Amendment provides for a fair allocation of the risk of such market conditions between the Owner and the Contractor and shall only apply to the Potentially Time and Price-Impacted Material(s) listed in Schedule A to this Amendment.
2. BASELINE PRICE AND TIME Owner and Contractor shall agree upon a method for establishing the market price as of the date of this Amendment ("Baseline Price") and the method for calculating an adjustment in the pricing for a Potentially Time and Price-Impacted Material listed in Schedule A to this Amendment.
2.1. Compensation for any Potentially Time and Price-Impacted Material shall not be duplicated in any contingency amounts established under the terms of the Agreement.
3. ADJUSTMENT IN BASELINE PRICE If during the course of the Project a Potentially Time and Price-Impacted Material item experiences an increase or decrease in its Baseline Price, either Party may notify the other in writing within thirty (30) Days from the date the basis for an equitable adjustment to the Contract Price, pursuant to article 8 of the Agreement, arises and shall provide appropriate documentation substantiating such adjustment. An adjustment in the pricing for a Potentially Time and Price-Impacted Material shall not include any amount for overhead and profit.

## Slide 12: ConsensusDocs® 200.1 (Cont’d) (emphasis added)
3.1. In the event of a decrease in a Baseline Price, the Contract Price shall be equitably adjusted to reflect such decrease, subject to section 3.3 of this Amendment, but only for those Potentially Time and Price-Impacted Materials delivered on or after the date on which written notice of the adjustment in Baseline Price is given.
3.2. In the event of an increase in a Baseline Price, the Contract Price shall be equitably adjusted to reflect such increase, subject to section 3.3 of this Amendment, but only for those Potentially Time and Price-Impacted Materials delivered on or after the date on which written notice of the adjustment in Baseline Price is given.
3.3. The Contract Price shall not be adjusted by more than ___% percent of the original Contract Price for the aggregate of the increases or decreases in Baseline Prices for Potentially Time and Price-Impacted Materials.
3.4. No adjustment shall be made for any quantities of Potentially Time and Price-Impacted Materials scheduled for delivery under the terms of the Agreement prior to the date on which written notice of the adjustment in Baseline Price is given, unless the failure to deliver such quantities before that date is beyond the control of and without the fault of the Contractor, its Subcontractors and Material Suppliers.
4. TIME-IMPACT AND AVAILABILITY If the Contractor is delayed at any time in the commencement or progress of the Work due to a delay in the delivery of, or unavailability of, a Potentially Time and Price-Impacted Material, beyond the control of and without the fault of the Contractor, its Subcontractors and Material Suppliers, the Contractor shall be entitled to an equitable extension of the Contract Time and an equitable adjustment of the Contract Price in accordance with section 6.3 of the Agreement. The Owner and Contractor shall undertake reasonable steps to mitigate the effect of such delays. Notwithstanding any other provision to the contrary, the Contractor shall not be liable to the Owner for any expenses, losses or damages arising from a delay in the delivery of a Potentially Time and Price-Impacted Material item not the fault of the Contractor, its Subcontractors and Material Suppliers.

## Slide 13: Defenses to Delay Claims
Notice
Not Critical
Concurrent
Lien Waiver Language
Pay App Language
Change Order Language

## Slide 14: Distinguishing Delay and Disruption Claims
Delay Claims versus Disruption/Loss of Productivity Claims
  With loss of productivity claims, it is irrelevant whether the impacted activities lie on the critical path - although loss of productivity is often a consequence of delay
  Loss of productivity is only concerned with unanticipated increases in costs incurred to perform any given work activity
  Productivity: A measurement of rate of output per unit of time or effort, usually measured in labor hours or equipment hours

## Slide 15: Essentials to Disruption/Loss of Productivity Claims
Elements for a loss of productivity claim
  Liability:
    Impacts due to errors and omissions in design documents (Design-Bid-Build)
    Impacts caused by having to perform work out-of-sequence
    Delays which push the project into periods of adverse weather conditions
    Effect of excessive overtime due to acceleration

## Slide 16: Essentials to Disruption/Loss of Productivity Claims (Cont’d)
  Causation
    Events were unforeseeable at time of subcontract or change order execution.
    Events were beyond claimant’s control.
    Events were caused by owner or design professional (Design-Bid-Build, not design-build contract if caused by design team).
    Events were caused by situations for which the owner assumed contractual liability, such as a force majeure or differing site conditions.

## Slide 17: Essentials to Disruption/Loss of Productivity Claims (Cont’d)
  Damages
    Must present a reasonably accurate estimate of losses.
    Not necessarily a precise calculation; but must utilize a methodology recognized by the courts/arbitrator.
    Start with Job Cost Report.

## Slide 18: Disruption and COVID-19
The COVID-19 pandemic and other factors have caused global disruptions to supply chains and labor markets, and caused subcontractors (as well as owners and contractors) to make difficult decisions as to how to proceed. For example, instead of accepting that an unforeseen disruptive event has necessitated a work stoppage, an owner and contractor may instruct subcontractors to proceed with the project, be as efficient as possible, and work around the impediments.
It is important for subcontractors to promptly convey and provide notice to the contractor that changes to the project may cause a decrease to productivity and increased costs.

## Slide 19: Proving Disruption Damages
Sample Methodologies
  Actual Cost Method
  Measured Mile
  Similar Work Comparison
  Specialty Industry Studies
  General Industry Studies
  Total Cost Method
    Modified Total Cost Method
    Probably need expert testimony

## Slide 20: Defenses to Disruption Claims
Notice
Job Cost Report
Lien Waiver Language
Pay App Language
Change Order Language

## Slide 21: Tips for Delay and Disruption Claims: An Overview
With the elements in mind, some common keys to claims to consider:
  Know the Subcontract Key Terms
  Provide Information to Plan the Project
  Follow the Subcontract and Plan
  Document
    Promptly document, communicate, and provide notice in daily reports, meeting minutes, scheduled updates, etc.
  Diagnose delay and productivity impacts early (RFIs/Rain Delays, etc.)

## Slide 22: Tips for Delay and Disruption Claims: An Overview
Traps to successful claims:
  A Subcontractor claim can be doomed by a lack of prior and proper planning and execution, by the Subcontract terms and conditions, or by not following the Subcontract

## Slide 23: Key Contractual Provisions
What contractual provisions impact time, delay, and disruption issues?
  Definitions of Substantial Completion/Time
  Date of Commencement
  Scheduling (i.e. Critical Path Method (CPM))
  Claim Provisions for Delays (Unexcused vs. Excused Delay)
  Concurrent Delays
  No Damages for Delay or Disruption Clauses

## Slide 24: Know the Contract; Is There Any Favorable Law?
Know the Contract/Subcontract:
  Provisions relative to the schedule of work
  Subcontractor’s ability to seek relief from changes to and impacts upon his work plan and schedule
  Notice and claims provisions
  A Subcontract that has an enforceable “ no damages for delay or disruption” clause may prevent the subcontractor from obtaining money as a result of delays or disruption
  Consider negotiating harmful terms and conditions away
  Obtain a copy of the Contract/Subcontract and understand the obligations before bidding or contracting
Is There Any Favorable Law?:
  Prompt Pay Act, Pay If Paid, Indemnity

## Slide 25: Scheduling Issues and Delays
Labor shortages and material supply issues can trigger a chain reaction causing delays and/or disruption.
If the owner/GC holds the substantial completion date firm, that usually results in major trade stacking for subcontractors, which may cause significant inefficiency.
When providing input into the schedule, consider scheduling in more float days for inevitable delays, and likely delays in obtaining permits from municipalities when developing/modifying the schedule.

## Slide 26: Key Considerations for Handling Delay and Disruption Claims
  Review the subcontract language that was agreed to and the work plan that was set.
  Review daily reports that address labor and other resource utilization, as well as any project conditions that have delayed or impacted contractor’s performance.
  Review written notices and meeting minutes regarding any delays or impacts.
  Follow up in a timely manner (and in the manner required by the Contract) to present a quantification of time and/or money sought as relief.

## Slide 27: Supporting Delay and Disruption Claims
Consider the form of evidence:
  Note and explain any deviations from the work plan in contemporaneous project records (and photos/videos)
    This is usually the most persuasive evidence.
  Actual costs directly attributable to the impact should be separately tracked throughout the project and presented
    The contractor/subcontractor typically has the burden of proving the delay impacted him, and the amount of his damages.

## Slide 28: Cumulative Impact Claims
Cumulative Impact
  In addition to the direct costs associated with implementing a change order, Contractors should beware of—and prepare for—the Cumulative Impact
What is “Cumulative Impact”
  The Construction Industry Institute provides this definition:
    When there are multiple changes on a project and they act in sequence or concurrently, there is a compounding effect - this is the most damaging consequence for a project and the most difficult to understand and manage. The net effect of the individual changes is much greater than a sum of the individual parts.
  In other words, when a project requires multiple change orders, there is a corresponding ripple effect. The Subcontractor may be required to:
    Tear out work already in place.
    Re-plan and re-sequence work that had previously been scheduled.
    Adjust the allocation of manpower.

## Slide 29: Cumulative Impact From Change Orders
Major Causes
  Work Flow Disruption, Out of Sequence
  Lack of Materials
  Same Work, Different Conditions
  Work Performed in Adverse Weather Conditions
  Significant Overtime

## Slide 30: Cumulative Impact Claims
Common keys for consideration:
  Reserve rights to the claim
    If the change order requests the number of days of delay, analyze whether you should state “zero.” The Cumulative Impact must be considered and accounted for.
  Be prepared with evidence to support that changes were excessive
  Be prepared to demonstrate the link between excessive change orders and the loss of productivity
    This is a difficult, but important element.
    Observe and document the ripple effect as change orders are executed.
    May need legal and consultant help.

## Slide 31: QUESTIONS?